## Gantt Chart
GANTT CHART
PROJECT TITLE |  | CETM46-Assignment | [5 empty] | COMPANY NAME | [7 empty] | University of Sunderland - MSc Data Science
PROJECT MANAGER |  | Jackie CHU Lai Ting (219265092) | [5 empty] | PROJECT PERIOD | [7 empty] | 3/5/22 - 11/7/22
WBS NUMBER | TASK TITLE | TASK OWNER | OTHER PARTICIPANT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | May | [25 empty] | June | [25 empty] | July
|  |  | OTHER PARTICIPANT |  |  |  |  | WEEK 1 | [5 empty] | WEEK 2 | [5 empty] | WEEK 3 | [5 empty] | WEEK 4 | [5 empty] | WEEK 5 | [5 empty] | WEEK 6 | [5 empty] | WEEK 7 | [5 empty] | WEEK 8 | [5 empty] | WEEK 9 | [5 empty] | WEEK 10 | [5 empty] | WEEK 11
[8 empty] | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S
 | time axis 2022-05-02 to 2022-07-16
1 | Project Conception and Initiation
1.1 | Research for suitable topic | Jackie Chu |  | 2022-05-03 | 2022-05-07 | 5 | 50% | bar: 2022-05-03 to 2022-05-14
1.2 | Topic domain study | Jackie Chu |  | 2022-05-04 | 2022-05-11 | 8 | 0% | bar: 2022-05-04 to 2022-05-14
1.3 | Data sources study | Jackie Chu |  | 2022-05-07 | 2022-05-11 | 5 | 0% | bar: 2022-05-07 to 2022-05-14
1.4 | Topic review and confirmation | Jackie Chu | Marta R | 2022-05-12 | 2022-05-12 | 1 | 0%
2 | Literature research
2.1 | Algorithms study | Jackie Chu |  | 2022-05-13 | 2022-05-28 | 16 | 0% | bar: 2022-05-09 to 2022-05-28
2.2 | Methodology to be chosen | Jackie Chu |  | 2022-05-30 | 2022-06-04 | 5 | 0% | bar: 2022-05-30 to 2022-06-04
2.3 | Prototype feasibility study | Jackie Chu |  | 2022-06-06 | 2022-06-18 | 13 | 0% | bar: 2022-06-06 to 2022-06-18
2.4 | Literature writing | Jackie Chu |  | 2022-06-06 | 2022-06-22 | 17 | 0% | bar: 2022-06-06 to 2022-06-22
2.5 | Interim review with Marta | Jackie Chu | Marta R | 2022-06-23 | 2022-06-23 | 1 | 0% | bar: 2022-06-23
2.6 | Assignment 1 consolidation | Jackie Chu |  | 2022-06-24 | 2022-06-25 | 2 | 0% | bar: 2022-06-24 to 2022-06-25
3 | Prototype Development
3.1 | Software study | Jackie Chu |  | 2022-06-06 | 2022-06-18 | 13 | 0% | bar: 2022-06-06 to 2022-06-18
3.2 | High level content design for assignment 2 | Jackie Chu |  | 2022-06-20 | 2022-06-20 | 1 | 0% | bar: 2022-06-20
3.3 | Review on the contents with Marta | Jackie Chu | Marta R | 2022-06-23 | 2022-06-23 | 1 | 0% | bar: 2022-06-23
3.4 | Data source extraction | Jackie Chu |  | 2022-05-13 | 2022-05-17 | 5 | 0% | bar: 2022-05-09 to 2022-05-17
3.5 | Model development | Jackie Chu |  | 2022-06-21 | 2022-06-25 | 5 | 0% | bar: 2022-06-21 to 2022-06-25
3.6 | Layout design | Jackie Chu |  | 2022-06-27 | 2022-06-28 | 2 | 0% | bar: 2022-06-27 to 2022-06-28
3.7 | Dashboard development | Jackie Chu |  | 2022-06-29 | 2022-07-02 | 4 | 0% | bar: 2022-06-29 to 2022-07-02
3.8 | Citation consolidation | Jackie Chu |  | 2022-07-04 | 2022-07-04 | 1 | 0% | bar: 2022-07-04
3.9 | Assignment 2 writing | Jackie Chu |  | 2022-06-28 | 2022-07-09 | 12 | 0% | bar: 2022-06-28 to 2022-07-09
3.1 | Assignment 2 consolidation | Jackie Chu |  | 2022-07-11 | 2022-07-11 | 1 | 0% | bar: 2022-07-11